## Reliable Project Schedule
Simulation of Reliable Construction Co. Project
[7 empty] | Activity |  | Range Name | Cell
|  | Immediate |  | Time Estimates |  | Start | Time | Finish | AFinish | I6
| Activity | Predecessor | o | m | p | Time | (triangular) | Time | AStart | G6
| A | – | 1 | 2 | 3 | 0 | 2 | 2 | ATime | H6
| B | A | 2 | 3.5 | 8 | 2 | 4.5 | 6.5 | BFinish | I7
| C | B | 6 | 9 | 18 | 6.5 | 11 | 17.5 | BStart | G7
| D | C | 4 | 5.5 | 10 | 17.5 | 6.5 | 24 | BTime | H7
| E | C | 1 | 4.5 | 5 | 17.5 | 3.5 | 21 | CFinish | I8
| F | E | 4 | 4 | 10 | 21 | 6 | 27 | CStart | G8
| G | D | 5 | 6.5 | 11 | 24 | 7.5 | 31.5 | CTime | H8
| H | E, G | 5 | 8 | 17 | 31.5 | 10 | 41.5 | DFinish | I9
| I | C | 3 | 7.5 | 9 | 17.5 | 6.5 | 24 | DStart | G9
| J | F, I | 3 | 9 | 9 | 27 | 7 | 34 | DTime | H9
| K | J | 4 | 4 | 4 | 34 | 4 | 38 | EFinish | I10
| L | J | 1 | 5.5 | 7 | 34 | 4.5 | 38.5 | EStart | G10
| M | H | 1 | 2 | 3 | 41.5 | 2 | 43.5 | ETime | H10
| N | K, L | 5 | 5.5 | 9 | 38.5 | 6.5 | 45 | FFinish | I11
[9 empty] | FStart | G11
[7 empty] | Project Completion | 45 | FTime | H11
[9 empty] | GFinish | I12
[9 empty] | GStart | G12
[9 empty] | GTime | H12
[9 empty] | HFinish | I13
[9 empty] | HStart | G13
[9 empty] | HTime | H13
[9 empty] | IFinish | I14
[9 empty] | IStart | G14
[9 empty] | ITime | H14
[9 empty] | JFinish | I15
[9 empty] | JStart | G15
[9 empty] | JTime | H15
[9 empty] | KFinish | I16
[9 empty] | KStart | G16
[9 empty] | KTime | H16
[9 empty] | LFinish | I17
[9 empty] | LStart | G17
[9 empty] | LTime | H17
[9 empty] | MFinish | I18
[9 empty] | MStart | G18
[9 empty] | MTime | H18
[9 empty] | NFinish | I19
[9 empty] | NStart | G19
[9 empty] | NTime | H19
[9 empty] | ProjectCompletion | I21